## Version History
Project Information
Project:
Client: | Infinite Computer Solutions
Start Date: | June 24, 2015
Team: | 25 Infinite Engineers
Date | Description | Version | Author | Reviewer
June 24, 2015 | Initial Version | 1 |  | Chandra
Note:
** Purpose: The purpose is to record the Business Processes and the Data Requirements along with Process to be executed

## Product Backlog
Product Backlog
User Story ID | Project | Business Process Title | Tasks | Priority | Sprint Details | Owner | Status
USID1 |  | Customer Interaction | Creating a Problem Statement | 1 | 1 |  | Open
USID2 |  | Architecture | Define the System and App Architecture | 1 | 2 |  | Open
USID3 |  | System Definition | Infrastructure Requirements Definition | 1 | 2 |  | Open
USID4 |  | Use Case Definition |  | 1 | 3 |  | Open
USID5 |  | Use Case Definition |  | 1 | 3 |  | Open
USID6 |  | Use Case Definition |  | 1 | 3 |  | Open
USID7 |  | Use Case Definition |  | 1 | 3 |  | Open

## Sprint TimeLines
Project Timelines
Sprint No | Title | Start Date | End Date | Duration | Effort - Total | Release Date | Review Date | Success Criteria | Remarks/Comments
1 | Spring 1 - Customer Interaction & Requirements Gathering | June 24, 2015 | June 26, 2015
2 | Sprint 2 - Application Architecture and System Definition | June 24, 2015 | June 29, 2015
3 | Sprint 3 - Prioritized User Story Implementation | June 25, 2015 | July 2, 2015
4 | Sprint 4 - Prioritized User Story Implementation | July 2, 2015 | July 7, 2015

## Sprint 1 Backlog
Sprint 1 BackLog
Task Id | Project | UserStory ID | User Story | Tasks | Resource | Estimated (Hrs) | Status
T1 |  | USID1 | Creating a Problem Statement | Preparing the problem statement |  |  | Open
T2 |  | USID1 | Creating a Problem Statement | Sending the problem statement for reviewing |  |  | Open
T3 |  | USID1 | Creating a Problem Statement | Approving the problem statement |  |  | Open
T4 |  | USID1 | Creating a Problem Statement | Finalize and approve the Problem Statement |  |  | Open
T5 |  | USID2 | Define the System and App Architecture | Define the System Architecture |  |  | Open
T6 |  | USID2 | Define the System and App Architecture | Define the Technology Stack |  |  | Open
T7 |  | USID2 | Define the System and App Architecture | Define the Application Architecture |  |  | Open
T8 |  | USID2 | Define the System and App Architecture | Identify the Layers and Components of the application |  |  | Open
T9 |  | USID2 | Define the System and App Architecture | Define the external APIs to be used |  |  | Open
T10 |  | USID2 | Define the System and App Architecture | Identify the Unit Testing Framework to be adopted |  |  | Open
T11 |  | USID3 | Base Architecture Implementation | Create the Project Structure with all Layers |  |  | Open
T12 |  | USID3 | Base Architecture Implementation | Create the Base Data Repository Architecture and Design |  |  | Open
T13 |  | USID3 | Base Architecture Implementation | Create the Models needed for Sprint 1 |  |  | Open
T14 |  | USID4 | Infrastructure Requirements Definition | Create Teams for SVN access |  |  | Open
T15 |  | USID4 | Infrastructure Requirements Definition | Set up SVN for project with team access |  |  | Open
T16 |  | USID4 | Infrastructure Requirements Definition | Set up Build and Release environment for project |  |  | Open
T17 |  | USID4 | Infrastructure Requirements Definition | Communicate to all Stakeholders about the Infra and SVN setup |  |  | Open

## Sprint 2 Backlog
Sprint BackLog
Task Id | UseStory ID | Project | User Story | Tasks | Resource | Effort (Hrs) | Status
T1 | USID4 |  |  | Sharing the requirement document with Infinite participants |  |  | Open
T2 | USID4 |  |  | Understanding Requirements and Preparing Clarification Log |  |  | Open
T3 | USID4 |  |  | Invite the necessary stakeholders |  |  | Open
T4 | USID4 |  |  | Product Owner/Infinite Internal Team will review and close all Clarification Log |  |  | Open
T5 | USID4 |  |  | Identifying the Functional Data |  |  | Open
T6 | USID4 |  |  | Creating Class & ER Diagram for the identified Functional Data |  |  | Open
T7 | USID4 |  |  | Creating Wireframes using HTML |  |  | Open
T8 | USID4 |  |  | Reviewing Wireframes |  |  | Open

## Sprint 3 Backlog
Sprint BackLog
Task Id | UseStory ID | Project | User Story | Tasks | Resource | Effort (Hrs) | Status
T1 | USID1 |  |  | Create the user story document |  |  | Open
T2 | USID1 |  |  | Create the Activity Diagram - flow for user story |  |  | Open
T3 | USID1 |  |  | Implement the Data Repository Interfaces, Classes and Models |  |  | Open
T4 | USID1 |  |  | Implement the Business Layer |  |  | Open
T5 | USID1 |  |  | Write unit tests for the BusinessLayer methods added |  |  | Open
T6 | USID1 |  |  | Create the controller for the UI defined |  |  | Open
T7 | USID1 |  |  | Write unit tests for controller |  |  | Open
T8 | USID1 |  |  | Create the HTML for the wireframe defined |  |  | Open

## Sprint 4 Backlog
Sprint BackLog
Task Id | UseStory ID | Project | User Story | Tasks | Resource | Effort (Hrs) | Status
T1 | USID4 |  |  | Integrate the controller and the view |  |  | Open
T2 | USID4 |  |  | Write the Functional Test Cases for User Story |  |  | Open
T3 | USID4 |  |  | Write the User Acceptance Test Cases for User Story |  |  | Open
T4 | USID4 |  |  | Validate Non-Functional Requirements |  |  | Open
T5 | USID4 |  |  | Integrate with the application |  |  | Open
T6 | USID4 |  |  | CheckIn Code and Unit Tests |  |  | Open
T7 | USID4 |  |  | Deploying the application |  |  | Open
T8 | USID4 |  |  | Project presentation |  |  | Open

## Resource_UCA
Resources Allocation
SrNo. | Employee Id | Name | Module | User Story Assigned For Sprint 1
1 | 1017138 | Vasavi N K
2 | 1017137 | Seetha H
3 | 1017127 | Roshan Kumar Sahu
4 | 1017130 | Prakash Kumar Singh
5 | 1017132 | Katyayani
6 | 1017143 | Sivaiah Kakarla
7 | 1017119 | Voore Vamshi
8 | 1017135 | Ajay Kandukoori
9 | 1017123 | Jaipal Kumar
10 | 1017118 | Paramesh Varahad
11 | 1017126 | Sachin Kumar
12 | 1017124 | Daitwa Anand
13 | 1017131 | Janardhan Reddy N
14 | 1017117 | Aakash Singh
15 | 1017122 | Mohd Irfan
16 | 1017121 | Santhosh Aageeru
17 | 1017133 | Sarah Rose Jonna
18 | 1017134 | Suresh S
19 | 1017120 | Saibaba Saheb SK
20 | 1017129 | Chandra Sekhar U
21 | 1017128 | Srikanth Naidu
22 | 1017125 | Siva Sankar V
23 | 1017139 | Gouthami S
24 | 1017136 | Deepak Nambardar
25 | 1305795 | Aishwarya Jain

## Resource_Details
Resources Information
SrNo. | Name | Contact No | Mail Id
1 | Vasavi N K
2 | Seetha H
3 | Roshan Kumar Sahu
4 | Prakash Kumar Singh
5 | Katyayani
6 | Sivaiah Kakarla
7 | Voore Vamshi
8 | Ajay Kandukoori
9 | Jaipal Kumar
10 | Paramesh Varahad
11 | Sachin Kumar
12 | Daitwa Anand
13 | Janardhan Reddy N
14 | Aakash Singh
15 | Mohd Irfan
16 | Santhosh Aageeru
17 | Sarah Rose Jonna
18 | Suresh S
19 | Saibaba Saheb SK
20 | Chandra Sekhar U
21 | Srikanth Naidu
22 | Siva Sankar V
23 | Gouthami S
24 | Deepak Nambardar
25 | Aishwarya Jain

## Miscellaneous
Project Repository Details |  |  | Configuration Details
SL. No | Name | Location | SL. No | Name | Branch | Location
1 | Code | Infinite Cloud | 1 | Application Name |  | Infinite Cloud
2 | Documents | Infinite Cloud | 2
3 | Design | Infinite Cloud | 3
4 |  |  | 4
5 |  |  | 5
Software CheckList |  |  | Hardware Checklist
SL. No | Name | Category | SL. No | Name | Category | Remarks
1 | Eclipse Luna | Java IDE | 1
2 | MySQL | Database | 2
3 | Jboss 5 | Application Server | 3
4 | JSF 1.2 | Deployment Dependencies | 4
5 |  |  | 5